## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | River Crossing below river bed by laying HDPE pipe with bed and bank anchoring arrangement at nodal point (NP: 63 to 64) of Irpala W/S Scheme within Ghatal Block under Ghatal Sub- Division of Midnapore Division, PHE Dte. (Length = 100.00 Mtr.) | AE Ghatal Sub-division |  | ORD/000918/2021-2022 | 537/MD | 22/03/2022 | 12/04/2022 | M/S. A.R. ENTERPRISE. | 11.39 | 10.7 | 93.92 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Quotation Bill of PH-II, Irhpala water supply scheme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000157/2022-2023 | 2003978660 | 06/07/2022 | 06/07/2023 | WBSEDCL | 0.46 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 200 Mtr. depth deep tube well by Direct Rotary Method for Head Work Site & 2nd tube well site of Irpala W/S Scheme with in Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000701/2021-2022 | 297/MD | 15/02/2022 | 02/03/2022 | ANNAPURNA TUBEWELL WORKS | 20.56 | 17.78 | 86.49 | 100
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Quotation Bill of PH-I, Irhpala water supply scheme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000156/2022-2023 | 2003978653 | 06/07/2022 | 06/07/2023 | WBSEDCL | 0.46 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 2508/MD | 09/12/2022 | 09/12/2022 | Resource Division | 48.91 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Quotation Bill of PH-I, Irhpala water supply scheme under MMD PHE Dte. |  |  | VCH/001782/2022-2023 | BP-2022-23-24 | 08/08/2022 | 08/08/2022 | WBSEDCL | 0.46 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Quotation Bill of PH-II, Irhpala water supply scheme under MMD PHE Dte. |  |  | VCH/001781/2022-2023 | BP-2022-23-25 | 08/08/2022 | 08/08/2022 | WBSEDCL | 0.46 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution pipe line and Rising main for IRPALA water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000175/2022-2023 | 400/AE/GSD | 11/07/2022 | 18/07/2022 | M/S. GEO | 4.85 | 4.85 | 100 | 0
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Construction of Retaining Wall at Head work site of IRPALA Water Supply Scheme under Ghatal Sub- Division PHE Dte. | AE Ghatal Sub-division |  | ORD/000471/2023-2024 | 5384/MD | 04/12/2023 | 19/12/2023 | A-PLUS | 6.31 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Irpala water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000223/2022-2023 | 1652/W/MMD | 12/08/2022 | 10/12/2022 | M/S. SAJAHAN CHOWDHURY | 11.79 | 11.58 | 98.28 | 100
11 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Restoration of damage shoulder & flank etc to the different roads under Midnapore Highway Division (Damage caused during laying pipe line by public Health Engineering Department. |  |  | BILL/00368/2022-2023 |  | 19/02/2023 | 19/02/2023 | EXECUTIVE ENGINEER, P.W.D | 138 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Laying distribution pipe line, Soil test and Construction of R.C.C. Elevated Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied works including supply of all labour & materials of IRPALA & its adjoining mouzas Water Supply Scheme within Ghatal Dev. Block under Ghatal sub-division of Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000473/2021-2022 | 2167/MD | 17/12/2021 | 22/05/2026 | M/S. A.R. ENTERPRISE. | 291.14 | 221.37 | 76.04 | 70
13 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | IRPALA Piped Water Supply Scheme. | SM/07386 | New | Construction of swith rooms and its boundary wall, laying rising main & accommodated FHTC etc. of Irpala Water Supply Scheme within Ghatal Block under Midnapore Division PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal),JE1 Ghatal Sub-division | ORD/000212/2022-2023 | 1677/MD | 12/08/2022 | 31/03/2026 | DULAL CHANDRA DAS | 111.18 | 58.44 | 52.56 | 60
Total | [13 empty] | 645.95 | 324.72 | 50.27