## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Pingla | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Khirinda Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001640/2022-2023 | 572/W/MMD | 20/03/2023 | 16/09/2023 | DEY ENTERPRISE | 25.26 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Pingla | Central Drilling | Khirinda Piped Water Supply Scheme. | SM/07393 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-I), PINGLA BLOCK UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000400/2022-2023 | 1720/CDD | 29/12/2022 | 28/01/2023 | UNIVERSAL ENTERPRISES | 5.62 | 4.78 | 85.03 | 0
3 | PASCHIM MEDINIPUR | Pingla | Central Drilling | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Hiring of Diesel driven motor cab(BS-III & Above) having contract carriage permit along with driver for the office of the Executive Engineer, CDD, PHE Dte. Car No. WB-04H-5846. |  |  | ORD/000431/2022-2023 | 33/S&WSD | 23/03/2023 | 22/04/2023 | ASHUTOSH DAS & CO | 0.14 | 0.26 | 180.29 | 100
4 | PASCHIM MEDINIPUR | Pingla | Central Drilling | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Water sample testing and other works for construction of tube well (300mm x 200mm x 200 mtrs depth) by utilising departmental machineries for khirinda w/s scheme (TW-II), Pingla block under Paschim Midnapore Distrrict, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000388/2022-2023 | 1723/CDD | 29/12/2022 | 28/01/2023 | SANKAR PRASAD DUTTA & CO. | 10.21 | 8.65 | 84.75 | 0
5 | PASCHIM MEDINIPUR | Pingla | Central Drilling | Khirinda Piped Water Supply Scheme. | SM/07393 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-II), PINGLA BLOCK, UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000389/2022-2023 | 1722/CDD | 29/12/2022 | 28/01/2023 | SANKAR PRASAD DUTTA & CO. | 5.6 | 4.74 | 84.66 | 0
6 | PASCHIM MEDINIPUR | Pingla | Central Drilling | Khirinda Piped Water Supply Scheme. | SM/07393 | New | WATER SAMPLE TESTING AND OTHER WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-I), PINGLA BLOCK UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000401/2022-2023 | 1721/CDD | 29/12/2022 | 28/01/2023 | UNIVERSAL ENTERPRISES | 10.23 | 8.77 | 85.75 | 0
7 | PASCHIM MEDINIPUR | Pingla | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Electric Quotation for TW-II of Khirinda W/S Scheme (Consumer ID 203971015) |  |  | BILL/00077/2023-2024 | BP-2023-24-33 | 04/05/2023 | 04/05/2023 | WBSEDCL | 2.69 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Pingla | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Electric quotation for Tw no-I of Khirinda w/s scheme ( Consumer ID-203972928) |  |  | BILL/00078/2023-2024 | BP-2023-24-34 | 04/05/2023 | 04/05/2023 | WBSEDCL | 2.63 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Pingla | Midnapore Mechanical | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
Total | [13 empty] | 72.8 | 27.2 | 37.36