## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate balance FHTC in 5 Nos. PWSS within Ghatal Sub-Division | SM/07876 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in RANAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000372/2020-2021 | 263/MD | 12/02/2021 | 14/03/2021 | KISHORE GHOSH | 9.49 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate balance FHTC in 5 Nos. PWSS within Ghatal Sub-Division | SM/07876 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000209/2020-2021 | 1430/MD | 26/11/2020 | 25/05/2021 | DIPAK KUMAR DOLAI | 94.96 | 0 | 0 | 0
Total | [13 empty] | 104.45 | 0 | 0