## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Pingla | Midnapore Division | Gopinathpur Piped Water Supply Scheme. | SM/07964 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1146/MD | 25/04/2023 | 25/04/2023 | Resource Division | 16.15 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Pingla | Midnapore Mechanical | Gopinathpur Piped Water Supply Scheme. | SM/07964 | New | Electric quotation for Gopinathpur PWSS Tube Well-II WS Scheme (Ref. ID 203917725) |  |  | BILL/00396/2022-2023 | BP-2022-23-144 | 24/03/2023 | 24/03/2023 | WBSEDCL | 0.49 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Pingla | Midnapore Mechanical | Gopinathpur Piped Water Supply Scheme. | SM/07964 | New | Electric quotation for Gopinathpur PWSS Tube Well-I WS Scheme (Ref. ID 203917726) |  |  | BILL/00395/2022-2023 | BP-2022-23-143 | 24/03/2023 | 24/03/2023 | WBSEDCL | 0.49 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Pingla | Midnapore Division | Gopinathpur Piped Water Supply Scheme. | SM/07964 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Gopinathpur W/S Scheme in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000471/2022-2023 | 2189/MD | 01/11/2022 | 30/04/2023 | BANERJEE CONSTRUCTION | 410.37 | 232.96 | 56.77 | 56
5 | PASCHIM MEDINIPUR | Pingla | Midnapore Mechanical | Gopinathpur Piped Water Supply Scheme. | SM/07964 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopinathpur Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001605/2022-2023 | 530/W/MMD | 20/03/2023 | 16/09/2023 | P.K.ENGINEERING | 22.78 | 21.15 | 92.83 | 50
6 | PASCHIM MEDINIPUR | Pingla | Midnapore Division | Gopinathpur Piped Water Supply Scheme. | SM/07964 | New | Laying of Rising main including interconnection pipeline for Gopinathpur W/S Scheme within Pingla block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Length - 350.00 Mtr.) | AE Kharagpur Sub-division |  | ORD/000313/2024-2025 | 3406/MD | 25/11/2024 | 09/01/2025 | MAA SARADA ENTERPRISE | 3.62 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Pingla | Midnapore Division | Gopinathpur Piped Water Supply Scheme. | SM/07964 | New | Laying additional distribution pipeline to accommodate FHTC & allied work for Gopinathpur PWSS under Pingla block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000327/2024-2025 | 3570/MD | 06/12/2024 | 19/02/2025 | ASHOK BANERJEE | 82.67 | 0 | 0 | 0
Total | [13 empty] | 536.57 | 254.11 | 47.36