## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000254/2020-2021 | 1450/MD | 26/11/2020 | 25/05/2021 | HARIPADA PATTANAYAK | 96.05 | 9.77 | 10.17 | 96
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000211/2020-2021 | 1431/MD | 26/11/2020 | 25/05/2021 | ASHIM KUMAR DEY | 93.67 | 5.11 | 5.46 | 80
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Panpara PWSS in Sabang Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk),JE RWS Kharagpur Sub-Division( Sabang) | ORD/000447/2020-2021 | 338/MD | 24/02/2021 | 01/07/2025 | BANERJEE CONSTRUCTION | 11.02 | 0 | 0 | 5
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Bural (Zone-I) PWSS, Block :- Sabang in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk),JE RWS Kharagpur Sub-Division( Sabang) | ORD/000437/2020-2021 | 308/MD | 22/02/2021 | 27/03/2026 | ASHOK BANERJEE | 93.36 | 27.01 | 28.93 | 70
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Construction of Boundary wall & land development with approach road for 2nd T.W. Site of Maligram & its adjoining mouzas W/S Scheme at Pingla Block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. (Total Length of the Boundary wall = 56.00 Mtr. & C/C distance of 250 X 250 mm size Column = 3.00 Mtr. & Height =2.45 Mtr. above GL) | AE Kharagpur Sub-division |  | ORD/000370/2020-2021 | 261/MD | 12/02/2021 | 29/03/2021 | SAKTI PADA BERA | 5.05 | 3.05 | 60.37 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Bural (Zone-II) PWSS, Block :- Sabang in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk),JE RWS Kharagpur Sub-Division( Sabang) | ORD/000436/2020-2021 | 307/MD | 22/02/2021 | 30/12/2025 | ASHOK BANERJEE | 53.72 | 0 | 0 | 45
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Beluria PWSS in Pingla Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000503/2020-2021 | 376/MD | 25/02/2021 | 27/03/2021 | M/S. A.R. ENTERPRISE. | 21.79 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Ragpur PWSS in Pingla Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang),JE1 Kharagpur Sub-division,JE3 Kharagpur Sub-division | ORD/000505/2020-2021 | 378/MD | 25/02/2021 | 01/01/2025 | GOBINDA MAITY | 9.25 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Chhotokhelna PWSS, Block :- Pingla in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000448/2020-2021 | 339/MD | 24/02/2021 | 05/04/2021 | ASHIM KUMAR DEY | 64.56 | 9.39 | 14.55 | 15
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Chandkuri (Zone-I) PWSS in Sabang Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000500/2020-2021 | 373/MD | 25/02/2021 | 27/03/2021 | DULAL CHANDRA DAS | 16.68 | 0 | 0 | 75
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Barsahara PWSS in Sabang Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000501/2020-2021 | 374/MD | 25/02/2021 | 12/03/2021 | MAMPI ENTERPRISE | 4.32 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Sartla PWSS in Sabang Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000502/2020-2021 | 375/MD | 25/02/2021 | 27/03/2021 | GOBINDA MAITY | 26.59 | 0 | 0 | 100
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Adasimla PWSS in Sabang Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000003/2021-2022 | 686/MD | 03/05/2021 | 17/06/2021 | SAI TUBE CO. | 34.29 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Bhikni Nischintapur PWSS, Block: - Sabang, in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000006/2021-2022 | 685/MD | 03/05/2021 | 28/05/2021 | SAI TUBE CO. | 45.46 | 12.13 | 26.67 | 30
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Khasbazar PWSS in Debra Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000544/2020-2021 | 420/MD | 26/02/2021 | 12/04/2021 | SUBRATA DAS | 31.59 | 20.83 | 65.94 | 67
16 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000007/2021-2022 | 684/MD | 03/05/2021 | 26/03/2025 | UTTAM KUMAR DAS | 94.86 | 38.86 | 40.97 | 76
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Narayanbar PWSS, Block: - Sabang, in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk),JE RWS Kharagpur Sub-Division( Sabang) | ORD/000375/2020-2021 | 266/MD | 12/02/2021 | 09/03/2021 | BANERJEE CONSTRUCTION | 49.06 | 0 | 0 | 5
18 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Gobardhanpur PWSS in Pingla Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000445/2020-2021 | 313/MD | 22/02/2021 | 23/12/2024 | DIPAK KUMAR BAKLY | 22.23 | 19.22 | 86.43 | 70
19 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Karkai PWSS in Pingla Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000504/2020-2021 | 377/MD | 25/02/2021 | 30/12/2024 | GOBINDA MAITY | 22.16 | 18.71 | 84.42 | 100
20 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Restoration of laying of distribution pipe line damage due to construction of road by PMGSY in different mouzas required for covering FHTC works of Maligram & its adjoining mouza Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000531/2021-2022 | 30/MD | 07/01/2022 | 06/02/2022 | HARIPADA PATTANAYAK | 18.99 | 2.19 | 11.54 | 95
21 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/001777/2021-2022 | BP-2021-22-524 | 25/03/2022 | 25/03/2022 | ASHIM KUMAR DEY | 15.66 | 0 | 0 | 0
22 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000275/2022-2023 | BP-2022-23-33 | 29/04/2022 | 29/04/2022 | SAI TUBE CO. | 12.05 | 0 | 0 | 0
23 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/001735/2021-2022 | BP-2021-22-475 | 16/03/2022 | 16/03/2022 | HARIPADA PATTANAYAK | 14.63 | 0 | 0 | 0
24 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 17 nos PWSS within Kharagpur Sub Diviion under Midnapore Division, PHE Dte. | SM/08079 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000101/2024-2025 | 3412/MD | 25/11/2024 | 25/11/2024 | Resource Division | 82.38 | 0 | 0 | 0
Total | [13 empty] | 939.43 | 166.27 | 17.7