## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pratappur PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000497/2020-2021 | 371/MD | 25/02/2021 | 12/03/2021 | DIPAK KUMAR DOLAI | 18.46 | 15.43 | 83.55 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Madhya Para in Pratappur PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000498/2020-2021 | 372/MD | 25/02/2021 | 12/03/2021 | SUBHASIS DOLAI | 9.63 | 7.98 | 82.86 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in RAJNAGAR (PASCHIM) PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000441/2020-2021 | 311/MD | 22/02/2021 | 24/03/2021 | ASHOK BANERJEE | 11.93 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Manikkundu in Bhabanipur PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000495/2020-2021 | 370/MD | 25/02/2021 | 12/03/2021 | SAMIT PAL | 12.53 | 11.23 | 89.64 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Birsingha PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000526/2020-2021 | 410/MD | 26/02/2021 | 13/03/2021 | SAMIT PAL | 6.95 | 6.7 | 96.4 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000529/2020-2021 | 413/MD | 26/02/2021 | 13/03/2021 | DEV KUMAR ADAK | 11.41 | 10.51 | 92.19 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in HAREKRISHNAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000655/2020-2021 | 450/MD | 26/02/2021 | 28/03/2021 | SUBHASIS DOLAI | 13.85 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhabanipur PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000527/2020-2021 | 411/MD | 26/02/2021 | 13/03/2021 | JIT ENTERPRISE | 15.04 | 13.63 | 90.58 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000528/2020-2021 | 412/MD | 26/02/2021 | 13/03/2021 | M/S JITEN BANARJEE | 11.44 | 10.16 | 88.79 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Electrical maintenance instrument for the O/F of the EE/MD, PHE Dte. |  |  | VCH/000580/2021-2022 | BP-2021-22-86 | 16/07/2021 |  | PULLOCK KUMAR GHOSH | 0.14 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Bhabanipur W/S Scheme within Chandrakona-I Dev. Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000479/2022-2023 | 2169/MD | 21/10/2022 | 20/11/2022 | SAMIT PAL | 17.77 | 12.41 | 69.81 | 100
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Bhabanipur W/S Scheme within Chandrakona-I Dev. Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. |  |  | BILL/00624/2023-2024 | BP-2023-24-246 | 23/08/2023 |  | SAMIT PAL | 5.25 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000714/2020-2021 | 97/AE/GSD | 25/02/2021 | 04/03/2021 | DEV KUMAR ADAK | 4.84 | 3.78 | 77.93 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dolai Para in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000717/2020-2021 | 99/AE/GSD | 25/02/2021 | 04/03/2021 | PBA INFRASTRUCTURE | 4.72 | 4.26 | 90.19 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 6 Nos. PWSS (Phase-I) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08203 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nandanpur-II in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000719/2020-2021 | 100/AE/GSD | 25/02/2021 | 04/03/2021 | PBA INFRASTRUCTURE | 4.76 | 4.24 | 89.11 | 0
Total | [13 empty] | 148.73 | 100.32 | 67.45