## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Chatra in Chatra PWSS of Garhbeta-II Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000519/2020-2021 | 392/MD | 25/02/2021 | 12/03/2021 | SUNIL DULE | 7.93 | 12.96 | 163.48 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Sutkujuri in Sutkijhuri PWSS of Garhbeta-II Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000520/2020-2021 | 393/MD | 25/02/2021 | 12/03/2021 | SUNIL DULE | 7.93 | 13.65 | 172.15 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Abashgarh Paschim Para in Abashgarh PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I). | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000524/2020-2021 | 409/MD | 26/02/2021 | 13/03/2021 | WATER LINK | 7.15 | 12.58 | 175.88 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza ¿ Bagmari, Bhabrigeria in Chaita PWSS of Salboni Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000518/2020-2021 | 391/MD | 25/02/2021 | 27/03/2021 | PRADIP KUMAR SAHA | 14.17 | 26.14 | 184.49 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Amrakuchi in Amrakuchi PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000521/2020-2021 | 406/MD | 26/02/2021 | 13/03/2021 | PULLOCK KUMAR GHOSH | 7.89 | 7.89 | 99.95 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Sekhuasol, Bhalukasol & Dalang in Dalang PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000522/2020-2021 | 407/MD | 26/02/2021 | 12/04/2021 | M/S. D.K.H.CONSTRUCTION | 29.01 | 54.39 | 187.5 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Pathra in Pathra PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000547/2020-2021 | 423/MD | 26/02/2021 | 28/03/2021 | SANJIT SINHA | 14.46 | 16.14 | 111.63 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Jagul, Raghabchak & Belpatri in Jagul PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000523/2020-2021 | 408/MD | 26/02/2021 | 12/04/2021 | DULAL CHANDRA DAS | 29 | 56.47 | 194.73 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Benashuli, Nayagram & Bhadute in Nayagram PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000546/2020-2021 | 422/MD | 26/02/2021 | 28/03/2021 | SANJIT SINHA | 19.29 | 24.71 | 128.11 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza - Sekhuasol, Bhalukasol & Dalang in Dalang PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) |  |  | VCH/000960/2020-2021 |  | 09/03/2021 | 09/03/2021 | M/S. D.K.H.CONSTRUCTION | 22 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC (left out) at different mouzas and shifting of pipeline in connection with widenening and strengthening of road for Chaita PWSS & its adjoining mouzas W/S Scheme within Midnapore Division ,PHE Dte. (SL No-06) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000138/2022-2023 | 280/AE/MSSD | 15/06/2022 | 15/07/2022 | AJITESH ACHARJEE | 3.98 | 3.66 | 91.93 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dalang W/S Scheme. |  |  | VCH/001927/2021-2022 | BP-2021-22-96 | 10/03/2022 | 10/03/2022 | M/S. D.K.H.CONSTRUCTION | 0.49 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Abashgarh Purba Para in Abashgarh PWSS in Midnapore Sadar Block in the District of Paschim Medinipore.(SL No-12) |  |  | VCH/001372/2021-2022 | BP-2021-22-413 | 24/02/2022 | 24/02/2022 | WATER LINK | 4.84 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dalang W/S Scheme. |  |  | VCH/001924/2021-2022 | BP-2021-22-96 | 10/03/2022 | 10/03/2022 | M/S. D.K.H.CONSTRUCTION | 1.28 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Lohamelya PWSS of Jhargram Block under Jhargram Division, PHE Dte. (Phase-II) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000067/2021-2022 | 1059/MD | 02/07/2021 | 17/07/2021 | NIMAI LAL GURIA | 7.53 | 0 | 0 | 1
16 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dhengasole Uttar Para in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-01) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000718/2020-2021 | 98/AE/MSSD | 24/02/2021 | 11/03/2021 | CHANDAN YADAV | 4.8 | 7.33 | 152.48 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Chaita in Chaita PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-04) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000675/2020-2021 | 96/AE/MSSD | 23/02/2021 | 10/03/2021 | AJITESH ACHARJEE | 4.81 | 7.31 | 151.89 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Jamdoba in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-09) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000725/2020-2021 | 103/AE/MSSD | 24/02/2021 | 11/03/2021 | A R ENTERPRISE | 1.96 | 2.3 | 116.87 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate balance FHTC in 13 Nos. PWSS (Phase-I) within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | SM/08204 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Godamouli in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SLN o-08) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000724/2020-2021 | 102/AE/MSSD | 24/02/2021 | 11/03/2021 | A R ENTERPRISE | 4.77 | 9.48 | 198.45 | 0
Total | [13 empty] | 193.3 | 255 | 131.92