## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. | SM/08205 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. 55/MD |  |  | VCH/001116/2020-2021 | 8443497 | 30/03/2021 | 30/03/2021 | SIRCON ENGINEERING SERVICES | 1.5 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. | SM/08205 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sutkijhuri, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000561/2020-2021 | 55/MD | 08/01/2021 | 18/01/2021 | SIRCON ENGINEERING SERVICES | 1.87 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Sutkujhuri Piped Water Supply Scheme to accommodate all FHTC. | SM/08205 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sutkujhuri PWSS to accommodate FHTC under JJM under Garhbeta-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000682/2021-2022 | 281/MD | 15/02/2022 | 17/03/2022 | MANISHIKA CONSTRUCTION | 21.78 | 0 | 0 | 100
Total | [13 empty] | 25.15 | 0 | 0