## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. | SM/08206 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. |  |  | VCH/001119/2020-2021 | 8443498 | 30/03/2021 | 30/03/2021 | SIRCON ENGINEERING SERVICES | 2.05 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. | SM/08206 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Jatra & Banshirasol, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000565/2020-2021 | 59/MD | 08/01/2021 | 18/01/2021 | SIRCON ENGINEERING SERVICES | 2.06 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. | SM/08206 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate FHTC (additional quantity) under JJM in Jatra Bansiraisol PWSS in Salboni block within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000550/2022-2023 | 2382/MD | 23/11/2022 | 03/12/2022 | PULLOCK KUMAR GHOSH | 1.82 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Jatra & Banshiraisol Piped Water Supply Scheme to accommodate all FHTC. | SM/08206 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Jatra & Banshiraisol PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000716/2021-2022 | 320/MD | 17/02/2022 | 18/04/2022 | PULLOCK KUMAR GHOSH | 44.93 | 0 | 0 | 100
Total | [13 empty] | 50.86 | 0 | 0