## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Basantapur PWSS Block Daspur-I District Paschim Medinipur | SM/08207 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Basantapur PWSS, Block ¿ Daspur-I in the district of Paschim Medinipur. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000533/2020-2021 | 417/MD | 26/02/2021 | 07/04/2021 | MASUM ALI KHAN | 95.51 | 94.14 | 98.57 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Basantapur PWSS Block Daspur-I District Paschim Medinipur | SM/08207 | Retrofitting | Continuation Work Order for the work of ?Retrofitting to accommodate FHTC under JJM for Basantapur PWSS, Block- Daspur-I in the district of Paschim Medinipur.? | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000169/2022-2023 | 1241/MD | 20/06/2022 | 11/07/2022 | MASUM ALI KHAN | 30.95 | 0 | 0 | 0
Total | [13 empty] | 126.46 | 94.14 | 74.44