## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. | SM/08208 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte.61/MD |  |  | VCH/001117/2020-2021 |  | 19/03/2021 | 19/03/2021 | SIRCON ENGINEERING SERVICES | 1.49 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. | SM/08208 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sitanathpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000567/2020-2021 | 61/MD | 08/01/2021 | 18/01/2021 | SIRCON ENGINEERING SERVICES | 1.57 | 2.88 | 183.09 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Sitanathpur Piped Water Supply Scheme to accommodate all FHTC. | SM/08208 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sitanathpur PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. (2nd Call) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000631/2021-2022 | 184/MD | 01/02/2022 | 18/03/2022 | DEBJIT PATRA | 25.18 | 14.33 | 56.93 | 75
Total | [13 empty] | 28.23 | 17.21 | 60.96