## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Bishnupur PWSS Block Sabang District Paschim Medinipur | SM/08209 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bishnupur PWSS, Block :- Sabang in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000440/2020-2021 | 310/MD | 22/02/2021 | 12/03/2024 | KISHORE GHOSH | 90.52 | 31.27 | 34.55 | 80
Total | [13 empty] | 90.52 | 31.27 | 34.55