## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dhaneswarpur PWSS Block-Pingla District Paschim Medinipur | SM/08210 | Retrofitting | Trial run of distribution system & rising main (CI/DI/HDPE/UPVC) with all related structure i.e.OHR etc. Dhaneswarpur and its adjoining mouza W/S Scheme within Pingla Block under Midnapore Division P.H.E. Dte. ( for 120 days). | AE Kharagpur Sub-division |  | ORD/000674/2021-2022 | 112/AE/KSD | 09/03/2022 | 13/03/2022 | GOBINDA MAITY | 1.14 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Dhaneswarpur PWSS Block-Pingla District Paschim Medinipur | SM/08210 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dhaneswarpur PWSS, Block - Pingla in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000532/2020-2021 | 416/MD | 26/02/2021 | 28/03/2021 | GOBINDA MAITY | 71.49 | 70.09 | 98.05 | 100
Total | [13 empty] | 72.63 | 70.09 | 96.51