## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. | SM/08211 | Retrofitting | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. |  |  | VCH/001115/2020-2021 | null | 19/03/2021 |  | SIRCON ENGINEERING SERVICES | 2.39 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. | SM/08211 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Ukhla Paschim Para in Ukhla PWSS (Part-B) in Garhbeta II Block in the District of Paschim Medinipore.(SL.NO-11) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000752/2020-2021 | 107/AE/MSSD | 26/02/2021 | 13/03/2021 | AJIJUR RAHAMAN MALLICK | 4.83 | 4.82 | 99.67 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. | SM/08211 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Ukhla PWSS to accommodate FHTC under JJM under Garhbeta -II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000683/2021-2022 | 282/MD | 15/02/2022 | 16/04/2022 | GOUTAM RAY | 43.53 | 38.95 | 89.5 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. | SM/08211 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Ukhla, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000562/2020-2021 | 56/MD | 08/01/2021 | 18/01/2021 | SIRCON ENGINEERING SERVICES | 2.49 | 2.39 | 96.03 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ukhla Piped Water Supply Scheme to accommodate all FHTC. | SM/08211 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Ukhla Purba Para in Ukhla PWSS in Garhbeta II Block in the District of Paschim Medinipore.(SL No-10) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000746/2020-2021 | 106/AE/MSSD | 26/02/2021 | 13/03/2021 | AJIJUR RAHAMAN MALLICK | 4.83 | 4.67 | 96.67 | 10
Total | [13 empty] | 58.07 | 50.83 | 87.54