## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Sauri Kotbar PWSS Block - Dantan-II District Paschim Medinipur | SM/08216 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sauri Kotbar PWSS, Block :- Dantan-II in the District of Paschim Medinipur. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000553/2020-2021 | 425/MD | 26/02/2021 | 07/04/2021 | TARUN KUMAR BHATTACHARYA | 89.08 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Sauri Kotbar PWSS Block - Dantan-II District Paschim Medinipur | SM/08216 | Retrofitting | Retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Sauri Kotbar & its adjoining mouzas W/S Scheme within Dantan-II Dev. Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000645/2022-2023 | 581/MD | 23/02/2023 | 25/03/2023 | DIPAK KUMAR BAKLY | 22.43 | 0 | 0 | 100
Total | [13 empty] | 111.51 | 0 | 0