## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Shanrpur PWSS Block - Debra District Paschim Medinipur | SM/08217 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Shanrpur PWSS, Block :- Debra in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000433/2020-2021 | 305/MD | 22/02/2021 | 03/04/2021 | UCON | 86.59 | 40.52 | 46.79 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Shanrpur PWSS Block - Debra District Paschim Medinipur | SM/08217 | Retrofitting | Preparation of DPR of Chhotokhena W/S Scheme. |  |  | VCH/001926/2021-2022 | BP-2021-22-280 | 16/03/2022 | 16/03/2022 | SIRCON ENGINEERING SERVICES | 0.06 | 0 | 0 | 0
Total | [13 empty] | 86.66 | 40.52 | 46.76