## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Mugbasan PWSS | SM/08218 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Mugbasan PWSS, Block - Keshpur in the district of Paschim Medinipur. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000070/2021-2022 | 1065/MD | 02/07/2021 | 01/08/2021 | MIDNAPUR PIPE CONCERN | 68.71 | 37.42 | 54.46 | 0
Total | [13 empty] | 68.71 | 37.42 | 54.46