## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS | SM/08219 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Satkui PWSS, Block - Kharagpur-I in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000531/2020-2021 | 415/MD | 26/02/2021 | 28/03/2021 | DULAL CHANDRA DAS | 61.89 | 44.47 | 71.86 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS | SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-III) | AE Kharagpur Sub-division |  | ORD/000889/2021-2022 | 106/AE/KSD | 09/03/2022 | 08/04/2022 | A-PLUS | 4.79 | 4.78 | 99.82 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS | SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-I) | AE Kharagpur Sub-division |  | ORD/000366/2021-2022 | 469/AE/KSD | 16/11/2021 | 16/12/2021 | M/S. GEO | 4.81 | 3.02 | 62.81 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS | SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-II) | AE Kharagpur Sub-division |  | ORD/000367/2021-2022 | 470/AE/KSD | 16/11/2021 | 16/12/2021 | M/S. GEO | 4.83 | 4.34 | 90 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Satkui PWSS | SM/08219 | Retrofitting | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-IV) | AE Kharagpur Sub-division |  | ORD/000544/2021-2022 | 107/AE/KSD | 09/03/2022 | 08/04/2022 | M/S. GEO | 4.61 | 4.5 | 97.62 | 0
Total | [13 empty] | 80.93 | 61.12 | 75.52