## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS | SM/08220 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Tararui W/S Scheme in the District of Paschim Medinipore. |  |  | BILL/00734/2022-2023 | BP-2022-23-345 | 01/02/2023 | 01/02/2023 | DIPAK KUMAR BAKLY | 1.54 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS | SM/08220 | Retrofitting | Laying of pipe line at Tararui East (Nimapada), Tararui Paschim (Ghosh Para) for supporting FHTC works of Tararui and its adjoining mouza W/S Scheme within Kharagpur Sub Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000213/2023-2024 | 455/RWS/MID | 10/08/2023 | 09/09/2023 | ASMA CONSTRUCTION | 1.22 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS | SM/08220 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Trarui PWSS, Block :- Dantan-I in the District of Paschim Medinipur. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),JE1 Kharagpur Sub-division | ORD/000439/2020-2021 | 309/MD | 22/02/2021 | 29/03/2021 | DIPAK KUMAR BAKLY | 74.94 | 25.66 | 34.24 | 98
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Tararui PWSS | SM/08220 | Retrofitting | Sinking of 150 X 100 mm dia. X 150 mtr. Depth Rig bored Tube wells for proposed additionally (boosting) to existing Tararui W/S Scheme, Dantan-I Block under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000108/2023-2024 | 2490/MD | 17/07/2023 | 01/08/2023 | M/S BAKLY CONSTRUCTION | 5.91 | 0 | 0 | 80
Total | [13 empty] | 83.62 | 25.66 | 30.69