## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Paschim Pathri PWSS to accommodate FHTC under JJM under Kharagpur-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000475/2021-2022 | 2169/MD | 17/12/2021 | 15/02/2022 | MAITY ENTERPRISE | 48.5 | 33.59 | 69.26 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Construction of Valve Chamber and Supplying, Fitting, Fixing G.I. Pipe including allied works at Paschim Pathri PWSS within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000218/2022-2023 | 519/AE/KSD | 18/08/2022 | 17/09/2022 | MAITY ENTERPRISE | 1.66 | 1.66 | 99.92 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Sinking of additional 150 X 100 mm dia. X 170 Mtr. Depth Rig bored Tube well for Paschim Pathri W/S Scheme under Kharagpur-I Dev. Block within Kharagpur Sub-Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000502/2022-2023 | 2413/MD | 25/11/2022 | 02/12/2022 | FIROJ KHAN | 5.47 | 5.13 | 93.76 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Paschim Pathri, Block - Kharagpur-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000568/2020-2021 | 63/MD | 11/01/2021 | 21/01/2021 | SIRCON ENGINEERING SERVICES | 2.22 | 4.32 | 194.69 | 0
Total | [13 empty] | 57.86 | 44.71 | 77.27