## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Paschim Pathri PWSS to accommodate FHTC under JJM under Kharagpur-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000475/2021-2022 | 2169/MD | 17/12/2021 | 15/02/2022 | MAITY ENTERPRISE | 48.5 | 33.59 | 69.26 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Construction of Valve Chamber and Supplying, Fitting, Fixing G.I. Pipe including allied works at Paschim Pathri PWSS within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000218/2022-2023 | 519/AE/KSD | 18/08/2022 | 17/09/2022 | MAITY ENTERPRISE | 1.66 | 1.66 | 99.92 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Sinking of additional 150 X 100 mm dia. X 170 Mtr. Depth Rig bored Tube well for Paschim Pathri W/S Scheme under Kharagpur-I Dev. Block within Kharagpur Sub-Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000502/2022-2023 | 2413/MD | 25/11/2022 | 02/12/2022 | FIROJ KHAN | 5.47 | 5.13 | 93.76 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Paschim Pathri, Block - Kharagpur-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000568/2020-2021 | 63/MD | 11/01/2021 | 21/01/2021 | SIRCON ENGINEERING SERVICES | 2.22 | 4.32 | 194.69 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Retrofitting of Ground Water Based Paschim Pathri Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Kharagpur-I block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08676 | Retrofitting | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well of Paschim Pathari to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000131/2023-2024 | 1351/W/MMD | 24/05/2023 | 14/07/2025 | DEBJYOTI BASU | 8.07 | 7.35 | 91.1 | 100
Total | [13 empty] | 65.93 | 52.06 | 78.97