## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08677 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Jharbhanga in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-03) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000740/2020-2021 | 100/AE/MSSD | 24/02/2021 | 11/03/2021 | CHANDAN YADAV | 4.82 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08677 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhengasole, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000566/2020-2021 | 60/MD | 08/01/2021 | 18/01/2021 | SIRCON ENGINEERING SERVICES | 2.08 | 1.82 | 87.66 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08677 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dhengasole Dakshinpara in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-02) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000723/2020-2021 | 99/AE/MSSD | 24/02/2021 | 11/03/2021 | CHANDAN YADAV | 4.72 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Dhengasole Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08677 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dhengasole Uttar Para in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-01) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000718/2020-2021 | 98/AE/MSSD | 24/02/2021 | 11/03/2021 | CHANDAN YADAV | 4.8 | 0 | 0 | 0
Total | [13 empty] | 16.42 | 1.82 | 11.09