## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Hatimasan Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08678 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Hatimasan PWSS to accommodate FHTC under JJM under Garhbeta-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000505/2021-2022 | 2247/MD | 28/12/2021 | 12/01/2022 | NIMAI HAZRA | 17.04 | 16.44 | 96.48 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Hatimasan Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/08678 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Hatimasan, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000570/2020-2021 | 65/MD | 11/01/2021 | 21/01/2021 | SIRCON ENGINEERING SERVICES | 1.91 | 3.47 | 182.11 | 0
Total | [13 empty] | 18.94 | 19.91 | 105.1