## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shyamsundarpur PWSS | SM/08695 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Shyamsundarpur PWSS (2nd Phase) in Sabang block in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000216/2021-2022 | 1449/MD | 03/09/2021 | 02/11/2021 | M/S. A.R. ENTERPRISE. | 122.79 | 151.85 | 123.66 | 75
Total | [13 empty] | 122.79 | 151.85 | 123.66