## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS (2nd Phase), Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000188/2021-2022 | 1464/MD | 07/09/2021 | 22/10/2021 | M/S. D.K.H.CONSTRUCTION | 73.12 | 109 | 149.08 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (2nd Phase), Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000231/2021-2022 | 1469/MD | 07/09/2021 | 17/09/2021 | M/S ZAMAN ENTERPRISE | 10.84 | 10.36 | 95.61 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhabanipur PWSS (2nd Phase), Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000207/2021-2022 | 1443/MD | 03/09/2021 | 18/09/2021 | SAMIT PAL | 23.91 | 31.98 | 133.76 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC 4 Nos. PWSS (Phase-II) within Ghatal Sub-Division under Midnapore Division, PHE Dte. | SM/08696 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pratappur PWSS (2nd Phase) in Ghatal Block in the district of Paschim Medinipur. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000210/2021-2022 | 1445/MD | 03/09/2021 | 02/11/2021 | DIPAK KUMAR DOLAI | 135.13 | 148.93 | 110.22 | 0
Total | [13 empty] | 242.99 | 300.27 | 123.57