## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Purulda PWSS, Block - Dantan-II in the district of Paschim Medinipur. | SM/08697 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Purulda PWSS, Block: - Dantan-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Sabang Blk) | ORD/000186/2021-2022 | 1466/MD | 07/09/2021 | 20/09/2025 | BANERJEE CONSTRUCTION | 90.08 | 43.4 | 48.18 | 15
Total | [13 empty] | 90.08 | 43.4 | 48.18