## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur | SM/09080 | Retrofitting | Electric Quotation bill for the WBSEDCL. |  |  | BILL/00317/2023-2024 | BP-2023-24-177 | 20/07/2023 |  | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 0.93 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur | SM/09080 | Retrofitting | Security Deposit/Caution money for electric quotation. [MB No:- 2948/MMD] {Shimulia W/S Scheme.} |  |  | BILL/00285/2023-2024 | null | 05/07/2023 |  | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 0.93 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Shimulia PWSS, Block - Ghatal, District - Paschim Medinipur | SM/09080 | Retrofitting | Retrofitting of Shimulia PWSS to accommodate FHTC in Ghatal block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000047/2022-2023 | 840/MD | 02/05/2022 | 01/06/2022 | ANUSKA ENTERPRISE | 26.82 | 24.59 | 91.67 | 100
Total | [13 empty] | 28.68 | 24.59 | 85.74