## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. | SM/09083 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Warda (Zone-II) PWSS under Kharagpur-II Block in Paschim Medinipur District. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000859/2021-2022 | 423/MD | 04/03/2022 | 03/04/2022 | S.T. ENTERPRISE | 38.17 | 36.7 | 96.14 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. | SM/09083 | Retrofitting | Retrofitting of Warda PWSS (Zone-II) to accommodate FHTC in Kharagpur- II block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-I) | ORD/000087/2022-2023 | 1134/MD | 13/06/2022 | 04/07/2022 | M/S. D.K.H.CONSTRUCTION | 24.23 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Warda PWSS, Block - Kharagpur-II, District - Paschim Medinipur. | SM/09083 | Retrofitting | Sinking of 10 nos. 125mm X 50mm dia & 140 Mtr. Depth tube well at different places of Midnapore Sadar Block under Standalone PWSS System for drought like situation prone blocks of Pachim Medinipur district (Mid-Term Plan under Master Plan) under Midnapore Division, PHE Dte.(Part2/4). |  |  | ORD/000138/2018-2019 | 423/MD | 08/03/2019 |  | M/S D.K.H.CONSTRUCTION | 17.1 | 23.12 | 135.24 | 0
Total | [13 empty] | 79.5 | 59.82 | 75.25