## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. | SM/09084 | Retrofitting | RESISTIVITY SURVEY AND OTHER WORKS OF MALLARPUR W/S SCHEME (TW-II), PINGLA BLOCK, PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000392/2022-2023 | 1683/CDD | 28/12/2022 | 27/01/2023 | M/S PS & ASSOCIATES | 5.85 | 4.79 | 81.9 | 0
2 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. | SM/09084 | Retrofitting | RESISTIVITY SURVEY AND OTHER WORKS OF MALLARPUR W/S SCHEME (TW-I), PINGLA BLOCK, UNDER PASCHIM MIDNAPOR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000385/2022-2023 | 1727/CDD | 29/12/2022 | 28/01/2023 | MENAKA ENTERPRISE | 6.19 | 5.37 | 86.74 | 0
3 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. | SM/09084 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN MALLARPUR TW-II, PASCHIM MEDINIPUR DISTRICT, UNDER CDD, PHE DTE. |  |  | ORD/000340/2022-2023 | 425/CMSD-I | 12/08/2022 | 27/08/2022 | UTTAM KUMAR CHATTERJEE | 4.95 | 4.3 | 86.78 | 0
4 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. | SM/09084 | Retrofitting | Hiring of Diesel driven motor cab(BS-III & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E PMU WBDWSIP under CMSD-I, CDD, PHE Dte. |  |  | ORD/000432/2022-2023 | 635/CMSD-I(D) | 26/12/2022 | 23/02/2023 | SIDDHARTHA CHATTERJEE | 0.29 | 0.51 | 176.16 | 0
5 | PASCHIM MEDINIPUR |  | Central Drilling | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. | SM/09084 | Retrofitting | PROVIDING DRIILING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SARBERYA W/S SCHEME (TW-I), UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000386/2022-2023 | 1726/CDD | 29/12/2022 | 28/01/2023 | MENAKA ENTERPRISE | 11.86 | 4.66 | 39.34 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Mallarpur PWSS, Block - Pingla, District - Paschim Medinipur. | SM/09084 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000098/2024-2025 | 3415/MD | 25/11/2024 | 25/11/2024 | Resource Division | 6.02 | 0 | 0 | 0
Total | [13 empty] | 35.16 | 19.63 | 55.84