## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sabang PWSS, Block - Sabang, District - Paschim Medinipur. | SM/09087 | Retrofitting | Extension of Pipeline at Mouza Gourbar Muslim Para within Sabang Augmentation Water Supply Scheme (Zone-I) at Sabang Block for FHTC Work under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000063/2022-2023 | 490/AE/KSD | 01/08/2022 | 31/08/2022 | PALASH KUMAR DAS | 4.7 | 4.28 | 91.15 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Sabang PWSS, Block - Sabang, District - Paschim Medinipur. | SM/09087 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sabang (Zone-I) PWSS under Sabang Block in Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000493/2021-2022 | 2186/MD | 17/12/2021 | 31/01/2022 | MASUM ALI KHAN | 53.37 | 39.45 | 73.92 | 0
Total | [13 empty] | 58.07 | 43.73 | 75.31