## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09107 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Khandibundh & Pathra in Pirakata PWSS in Salboni Block District :-Paschim Medinipore within Midnapore Division PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000524/2021-2022 | 675/AE/MSSD | 24/12/2021 | 08/01/2022 | DEBJIT PATRA | 4.48 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09107 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza Khadibandh in Pirakata PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-06) |  |  | VCH/001770/2021-2022 | BP-2021-22-516 | 25/03/2022 | 25/03/2022 | DEBJIT PATRA | 1.02 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09107 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Pirakata, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000564/2020-2021 | 58/MD | 08/01/2021 | 18/01/2021 | SIRCON ENGINEERING SERVICES | 3.68 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09107 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Pirakata PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000481/2021-2022 | 2175/MD | 17/12/2021 | 31/01/2022 | SANJIT SINHA | 52.54 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Rerofitting of Ground Water Based Pirakata Pipe Water Supply Scheme to accommodate FHTC under Jal Sapno Mission under Salboni block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09107 | Retrofitting | Sinking of Rig bored Tube well of 150 X 100 mm dia. X 200 Mtr. Depth for boosting perpose of Pirakata Water supply Scheme under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000339/2023-2024 | 700/AE/MSSD | 06/10/2023 | 21/10/2023 | SANJIT SINHA | 7.01 | 0 | 0 | 100
Total | [13 empty] | 68.73 | 0 | 0