## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Dhamsai Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09418 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Dhamsai PWSS, Block - Keshpur in the district of Paschim Medinipur. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000482/2021-2022 | 2176/MD | 17/12/2021 | 16/01/2022 | PRADIP KUMAR SAHA | 20.61 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Dhamsai Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09418 | Retrofitting | Laying of distribution system of uPVC pipeline due to damage portion road along the pipeline and including shifting under Dhamsai W/S Scheme in Keshpur Block under Midnapore Division, PHE Dte. |  |  | VCH/001141/2021-2022 | BP-2021-22-356 | 08/02/2022 | 08/02/2022 | M/S. D.K.H.CONSTRUCTION | 6 | 0 | 0 | 0
Total | [13 empty] | 26.61 | 0 | 0