## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & its adjoining mouzas within Midnapore Division, PHE Dte. (Phase-F) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000080/2022-2023 | 1069/MD | 03/06/2022 | 24/06/2022 | MAITY ENTERPRISE | 22.04 | 20.79 | 94.34 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Construction of R.C.C. Over Head Reservoir (Raft Foundation) of capacity 600 CuM and staging height 20.00 mtr. as per approved drawing (PC-I/OHR/13/2012) with allied works under Goaltore Augmentation W/S Scheme within Garhbeta-II Block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. |  |  | VCH/001794/2021-2022 | BP-2021-22-544 | 29/03/2022 | 29/03/2022 | ASHIM KUMAR DEY | 20 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-D) (SL No-04) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000608/2022-2023 | 799/AE/MSSD | 10/01/2023 | 25/01/2023 | RUPKUMAR KARMAKAR | 4.67 | 4.3 | 92.23 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-C) (SL No-03) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000607/2022-2023 | 798/AE/MSSD | 10/01/2023 | 25/01/2023 | CHANDAN YADAV | 4.67 | 4.44 | 95.2 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-B) (SL No-02) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000606/2022-2023 | 797/AE/MSSD | 10/01/2023 | 25/01/2023 | ARNAB PATRA | 4.67 | 4.66 | 99.9 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-A) (SL No-01) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000605/2022-2023 | 794/AE/MSSD | 10/01/2023 | 25/01/2023 | A R ENTERPRISE | 4.66 | 4.64 | 99.37 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Goaltore, Block - Garhbeta-II) to be Retrofitting under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000115/2021-2022 | 994/MD | 23/06/2021 | 03/07/2021 | SIRCON ENGINEERING SERVICES | 3.8 | 3.8 | 100 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-E) (SL No-05) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000609/2022-2023 | 804/AE/MSSD | 11/01/2023 | 26/01/2023 | JIT ENTERPRISE | 4.62 | 4.46 | 96.54 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Laying of Rising main & interconnection pipeline for Augmentation of Goaltore & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length - 950.00 Mtr.) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000053/2024-2025 | 2448/MD | 08/08/2024 | 22/09/2024 | ARNAB PATRA | 7.64 | 4.85 | 63.48 | 50
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Goaltore Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Garhbeta-II block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09421 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & its adjoining mouzas within Midnapore Division, PHE Dte. (Phase-G) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-I),JE1 Sadar Sub-division | ORD/000081/2022-2023 | 1070/MD | 03/06/2022 | 27/06/2025 | MAITY ENTERPRISE | 72.11 | 15.02 | 20.83 | 20
Total | [13 empty] | 148.88 | 66.97 | 44.98