## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Khairullachak (Block-Midnapore Sadar) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/001037/2021-2022 | 1645/MD | 22/09/2021 | 02/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.56 | 1.56 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 2275/MD | 31/12/2021 | 31/12/2021 | Resource Division | 12.33 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Laying distribution pipe line, soil test, FHTC & construction of R.C.C. Over Head Reservoir of capacity 150 Cum and staging height 20.00 mtr. with allied work including Sinking of Deep Tube Well of 250 mm x 150 mm x250 m for Augmentation of Khairullachak W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000008/2022-2023 | 605/MD | 04/04/2022 | 01/10/2022 | BANERJEE CONSTRUCTION | 411.2 | 281.59 | 68.48 | 21
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 2474/MD | 06/12/2022 | 06/12/2022 | Resource Division | 13.36 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC. Block - Midnapore. District - Paschim Medinipur. |  |  | VCH/000462/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 12.33 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000020/2023-2024 | 1135/W/MMD | 12/04/2023 | 09/10/2023 | SUBHASIS ROY | 11.32 | 10.5 | 92.84 | 100
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 218/MD | 16/01/2023 | 16/01/2023 | Resource Division | 9.39 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Restoration of road shoulder flank etc. after laying pipeline by PHE Deptt. At NL Khan Link Road from 3.10 km to 4.20 km under PWD, Midnapur Division, in the district of Paschim Medinipur during the year 2022-23 |  |  | BILL/00369/2022-2023 | BP-2022-23-631 | 23/02/2023 | 23/02/2023 | EXECUTIVE ENGINEER, P.W.D | 10 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Electric Quation for Khairullachaki PWSS Tube well-II in connection Mohanpur CCC. |  |  | BILL/00006/2023-2024 | BP-2023-24-12 | 24/04/2023 | 24/04/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.27 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Construction of Chlorine storage room for Midnapore Sadar Sub-Division Store at Narampur P.H.E. Complex under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000069/2024-2025 | 2661/MD | 29/08/2024 | 28/10/2024 | PULLOCK KUMAR GHOSH | 5 | 0 | 0 | 60
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. | SM/09431 | Augmentation | Construction of 1 (One) No. 5.40 X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Augmentation of Khairullachak & its adjoining mouzas PWSS in block - Midnapore Sadar, District - Paschim Medinipur (Type-B). | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000845/2023-2024 | 806/MD | 15/03/2024 | 14/05/2024 | BENGAL TRADERS | 7.12 | 5.22 | 73.31 | 91
Total | [13 empty] | 493.87 | 298.88 | 60.52