## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | SM/09439 | New | Service connection charge of WBSEDCL at Dantarda, Chandkuri | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001027/2021-2022 | 2003775012/Quot/03 | 16/12/2021 | 16/12/2022 | WBSEDCL | 0.13 | 0.13 | 100 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | SM/09439 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Dontarda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001173/2021-2022 | 119/W/MMD | 24/01/2022 | 24/05/2022 | DEBKUMAR BASU | 6.52 | 3.87 | 59.36 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | SM/09439 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Dontarda water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001135/2021-2022 | 2507/W/MMD | 30/11/2021 | 04/12/2021 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | SM/09439 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001816/2021-2022 | BP-2021-22-505 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.08 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | SM/09439 | New | Sinking of different Tube-well. |  |  | VCH/001806/2021-2022 | BP-2021-22-523 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.66 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dontarda Mouzas | SM/09439 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Dontarda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000486/2021-2022 | 2179/MD | 17/12/2021 | 16/05/2022 | MIDNAPUR PIPE CONCERN | 31.32 | 28.42 | 90.73 | 100
Total | [13 empty] | 50.19 | 32.42 | 64.59