## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | Service connection charge of WBSEDCL at Talda, Sabang | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001028/2021-2022 | 2003774985/Quot/03 | 16/12/2021 | 16/12/2022 | WBSEDCL | 0.13 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Talda water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001137/2021-2022 | 2511/W/MMD | 30/11/2021 | 04/12/2021 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | Service connection charges of WBSEDCL |  |  | VCH/001118/2022-2023 | BP-2021-22-57 | 22/04/2022 | 22/04/2022 | WBSEDCL | 1.15 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Talda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte.(w/O No. 122/W/MMD dt. 24-01-2022) |  |  | VCH/001764/2022-2023 | BP-2022-23-42 | 12/08/2022 | 12/08/2022 | S.S.GHORAI | 0.71 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | Providing and installation of Pumping Machinery and other electromechanical equipment at newly sunk T/W at Talda, Block- Sabang under Ground bored Mini Piped W/S Scheme Dist- Paschim Medinipur under MMD,P.H.E.Dte.(W/O No. 122/W/MMD dt. 24-01-2022)(T.No. 1206 of 21-22) |  |  | VCH/001769/2022-2023 | BP-2022-23-36 | 12/08/2022 | 12/08/2022 | S.S.GHORAI | 0.44 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Talda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001176/2021-2022 | 122/W/MMD | 24/01/2022 | 24/05/2022 | S.S.GHORAI | 6.55 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | onstruction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Talda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. |  |  | BILL/00719/2022-2023 | BP-2022-23-407 | 01/02/2023 | 01/02/2023 | MIDNAPUR PIPE CONCERN | 18.52 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Talda Mouzas | SM/09440 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Talda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000488/2021-2022 | 2181/MD | 17/12/2021 | 16/05/2022 | MIDNAPUR PIPE CONCERN | 32.63 | 0 | 0 | 10
Total | [13 empty] | 64.59 | 0 | 0