## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Service connection charge of WBSEDCL at Dantarda, Batitaki, Chandkuri | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001029/2021-2022 | 2003774979/Quot/03 | 16/12/2021 | 16/12/2022 | WBSEDCL | 0.13 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Service connection charge of WBSEDCL at Nowgan, Sabang | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001031/2021-2022 | 2003774953/Quot/03 | 16/12/2021 | 16/12/2022 | WBSEDCL | 0.13 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Service connection charge of WBSEDCL at Now gan, Sabang | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001035/2021-2022 | 2003774945/Quot/03 | 16/12/2021 | 16/12/2022 | WBSEDCL | 0.13 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Dantardabatitaki, (ii) Fate Chak & (iii) Haripura of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000450/2021-2022 | 1277/MD | 05/08/2021 | 15/08/2021 | GOBINDA MAITY | 4.36 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Dantardabatitaki, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001174/2021-2022 | 120/W/MMD | 24/01/2022 | 24/05/2022 | ECO ENTERPRISE | 6.51 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Dantardabatitaki water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001130/2021-2022 | 2505/W/MMD | 30/11/2021 | 04/12/2021 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Quotation for service connection charges of WBSEDCL at Nilot Bhemua | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001520/2021-2022 | 2003855203/Quot/03 | 10/03/2022 | 10/03/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001815/2021-2022 | BP-2021-22-505 | 22/03/2022 | 22/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.82 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme For Dantardabatitaki Mouzas | SM/09441 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Dantardabatitaki, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000485/2021-2022 | 2178/MD | 17/12/2021 | 16/05/2022 | MIDNAPUR PIPE CONCERN | 26.09 | 0 | 0 | 90
Total | [13 empty] | 45.76 | 0 | 0