## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC. Block - Dantan-I. District - Paschim Medinipur. |  |  | VCH/000460/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.64 | 0 | 0 | 0
2 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 2276/MD | 31/12/2021 | 31/12/2021 | Resource Division | 2.64 | 0 | 0 | 0
3 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 1369/MD | 02/05/2023 | 02/05/2023 | Resource Division | 12.34 | 0 | 0 | 0
4 |  |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Electric quatation for New service connection at Sijua T.W.No-II (Ref Id-203987545) |  |  | BILL/00113/2023-2024 | BP-2023-24-40 | 15/05/2023 | 15/05/2023 | WBSEDCL | 4.17 | 0 | 0 | 0
5 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Laying balance quantity of pipe line & accommodate FHTC (21 Nos.) with allied works for Augmentation of Sarta-Sijua W/S Scheme under Dantan-I block within Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000103/2024-2025 | 2849/MD | 09/09/2024 | 24/10/2024 | PROVAT KUMAR DE | 11.96 | 0 | 0 | 85
6 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Laying of (Left out & Damaged) Distribution pipe line including Supply of Valves for Augmentation Sarta-Sijua Pipe Water Supply Scheme in Dantan-I Block under Khargapur Sub-Division within Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000289/2023-2024 | 3906/MD | 27/09/2023 | 11/11/2023 | PROVAT KUMAR DE | 10.22 | 9.65 | 94.44 | 95
7 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Laying Rising Main system including inter-connection and By-Pass arrangement for Augmentation Sarta-Sijua PWSS in Dantan-I Block under Khargapur Sub-Division of Midnapur Division PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000380/2023-2024 | 4042/MD | 11/10/2023 | 10/11/2023 | PROVAT KUMAR DE | 3.27 | 2.25 | 68.63 | 95
8 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 100 Cum and staging height 20.00 mtr. with allied work including Sinking of 250mm x 150mm x 190m deep tube well for Augmentation of Sarta-Sijua W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000375/2022-2023 | 1958/MD | 20/09/2022 | 19/03/2023 | PROVAT KUMAR DE | 111.93 | 95.77 | 85.56 | 99
9 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Cleaning the Chokage of pipe in the existing line at Sarta-Sijua PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000048/2024-2025 | 2246/AE/HQ/MD | 22/07/2024 | 01/08/2024 | PULLOCK KUMAR GHOSH | 0.9 | 0.9 | 99.91 | 100
10 |  |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Repairing of 2nd Pump House & Boundary wall for Sarta-Sijua PWSS within Dantan-I block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000500/2024-2025 | 570/AE/HQ/MD | 28/02/2025 | 29/04/2025 | PROVAT KUMAR DE | 3.65 | 0 | 0 | 100
11 |  |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. |  |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001291/2022-2023 | 2294/W/MMD | 29/12/2022 | 01/06/2024 | P.K.ENGINEERING | 11.44 | 10.64 | 93.01 | 20
Total | [13 empty] | 175.14 | 119.2 | 68.06