## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Continuation work order for the work of Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at different Places of Kharagpur Sub-Division Stores / Office premises stackyard etc. under Midnapore Division, PHE Dte. [For the period 4 months i.e. from 01.04.2021 to 31.07.2021] [Considering Zone - 'A' as per Joint Labour Commissioner order vide Memo No. - 352 /Stat/2RW/76/266/LCS/JLC, Dated - 27.12.2019] | AE Ghatal Sub-division |  | ORD/000850/2020-2021 | 606/MD | 30/03/2021 | 30/07/2021 | M/S. OXFORD SECURITY SERVICE | 3.75 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Ranirbazar (Block-Ghatal) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/001039/2021-2022 | 1647/MD | 22/09/2021 | 02/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.02 | 1.02 | 100 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Electric quotation Ghatal CCC at Ranisimulia, Ranirbazar Water supply scheme under MMD PHE Dte |  |  | VCH/002770/2022-2023 | BP-2022-23-58 | 23/11/2022 | 23/11/2022 | WBSEDCL | 0.3 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Purchasing of materials for the augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal. District - Paschim Medinipur. |  |  | VCH/000459/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 13.67 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-II under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001133/2022-2023 | 2114/W/MMD | 28/11/2022 | 28/03/2023 | M/S EMMESS | 11.37 | 10.1 | 88.82 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-III under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001076/2022-2023 | 1968/W/MMD | 20/10/2022 | 17/02/2023 | BUSR ENGINEERING | 10.79 | 10.51 | 97.47 | 99
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Exigency basis laying casing pipe under Bitumineous pucca road crosssing (Near Baliaghata bus stop,Bablatola Maruti Showroom,Chanak para Soni Mandir) of Khakurda to Ghatal PWD Road of Ranapur W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division |  | ORD/000524/2022-2023 | 171/AE/GSD | 01/04/2022 | 03/04/2022 | ANNAPURNA TUBEWELL WORKS | 3.64 | 3.48 | 95.6 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 2278/MD | 31/12/2021 | 31/12/2021 | Resource Division | 13.67 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 225/MD | 02/02/2023 | 02/02/2023 | Resource Division | 74.42 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Chandrakona to Ghatal Road from Chainage 36.600 Kmp to 42.00 Kmp Restoration of damages due to laying of proposed underground pipeline by PHE Deptt in the district of Paschim Medinipur. |  |  | BILL/00126/2023-2024 | BP-2023-24-81 | 08/05/2023 | 08/05/2023 | EXECUTIVE ENGINEER, P.W.D | 80 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Supply of C.I.D.F. Sluice valve C.I.Jeffy coupler for distribution and rising main pipe line for Augmentation of Ranirbazar water supply scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000644/2022-2023 | 108/AE/GSD | 13/02/2023 | 02/08/2023 | M/S. GEO | 3.59 | 0 | 0 | 100
Total | [13 empty] | 216.21 | 25.11 | 11.61