## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Continuation work order for the work of Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at different Places of Kharagpur Sub-Division Stores / Office premises stackyard etc. under Midnapore Division, PHE Dte. [For the period 4 months i.e. from 01.04.2021 to 31.07.2021] [Considering Zone - 'A' as per Joint Labour Commissioner order vide Memo No. - 352 /Stat/2RW/76/266/LCS/JLC, Dated - 27.12.2019] | AE Ghatal Sub-division |  | ORD/000850/2020-2021 | 606/MD | 30/03/2021 | 30/07/2021 | M/S. OXFORD SECURITY SERVICE | 3.75 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Ranirbazar (Block-Ghatal) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/001039/2021-2022 | 1647/MD | 22/09/2021 | 02/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.02 | 1.02 | 100 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 2278/MD | 31/12/2021 | 31/12/2021 | Resource Division | 13.67 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Laying distribution pipe line, Pump House, FHTC & construction of R.C.C. Over Head Reservoir of capacity 350 Cum (including Pile) and staging height 20.00 mtr. with allied work including Sinking of Deep Tube Well for Augmentation of Ranirbazar and its adjoining mouzas W/S Scheme in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000009/2022-2023 | 606/MD | 04/04/2022 | 19/11/2026 | M/S. A.R. ENTERPRISE. | 448.8 | 160.15 | 35.68 | 40
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-II under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001133/2022-2023 | 2114/W/MMD | 28/11/2022 | 28/03/2023 | M/S EMMESS | 11.37 | 10.1 | 88.82 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-III under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001076/2022-2023 | 1968/W/MMD | 20/10/2022 | 17/02/2023 | BUSR ENGINEERING | 10.79 | 10.51 | 97.47 | 99
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Exigency basis laying casing pipe under Bitumineous pucca road crosssing (Near Baliaghata bus stop,Bablatola Maruti Showroom,Chanak para Soni Mandir) of Khakurda to Ghatal PWD Road of Ranapur W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division |  | ORD/000524/2022-2023 | 171/AE/GSD | 01/04/2022 | 03/04/2022 | ANNAPURNA TUBEWELL WORKS | 3.64 | 3.48 | 95.6 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Electric quotation Ghatal CCC at Ranisimulia, Ranirbazar Water supply scheme under MMD PHE Dte |  |  | VCH/002770/2022-2023 | BP-2022-23-58 | 23/11/2022 | 23/11/2022 | WBSEDCL | 0.3 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Purchasing of materials for the augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal. District - Paschim Medinipur. |  |  | VCH/000459/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 13.67 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Supply of C.I.D.F. Sluice valve C.I.Jeffy coupler for distribution and rising main pipe line for Augmentation of Ranirbazar water supply scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000644/2022-2023 | 108/AE/GSD | 13/02/2023 | 02/08/2023 | M/S. GEO | 3.59 | 0 | 0 | 100
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Laying of Rising Main including interconnection of Augmentation of Ranirbazar & its adjoining mouzas W/S Scheme of Ghatal block under Ghatal Sub-Division within Midnapore Division, P.H.E. Dte. (Length- 2,470 Mtr.) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000593/2022-2023 | 344/MD | 31/01/2023 | 14/07/2026 | A-PLUS | 9.63 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 225/MD | 02/02/2023 | 02/02/2023 | Resource Division | 74.42 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Chandrakona to Ghatal Road from Chainage 36.600 Kmp to 42.00 Kmp Restoration of damages due to laying of proposed underground pipeline by PHE Deptt in the district of Paschim Medinipur. |  |  | BILL/00126/2023-2024 | BP-2023-24-81 | 08/05/2023 | 08/05/2023 | EXECUTIVE ENGINEER, P.W.D | 80 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal, District - Paschim Medinipur. | SM/09585 | Augmentation | Cutting concrete & bitumen road for Laying Rising main & Distribution pipeline for Augmentation of Ranirbazar W/S Scheme within Ghatal block under Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000842/2023-2024 | 638/MD | 06/03/2024 | 16/12/2024 | A-PLUS | 12.82 | 0 | 0 | 0
Total | [13 empty] | 687.45 | 185.25 | 26.95