## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Quotation for service connection charges of WBSEDCL at Neziveri | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001523/2021-2022 | 2003855194/Quot/03 | 10/03/2022 | 10/03/2023 | WBSEDCL | 0.13 | 0.13 | 100 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Purchasing of Materials. |  |  | VCH/001692/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.58 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. |  |  | VCH/000455/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.58 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Lejibheri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001194/2021-2022 | 153/W/MMD | 31/01/2022 | 31/05/2022 | DEBJYOTI BASU | 6.51 | 6.39 | 98.11 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at LEJIBHERI water supply scheme, of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001291/2021-2022 | 2516/W/MMD | 30/11/2021 | 04/12/2021 | OSMAN SEKH | 4.47 | 3.52 | 78.84 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Preparation of D.P.Rs. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Mangrajpur & (ii) Lejibheri of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000422/2021-2022 | 1336/MD | 18/08/2021 | 28/08/2021 | GOBINDA MAITY | 2.79 | 0 | 0 | 10
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 2116/MD | 13/12/2021 | 13/12/2021 | Resource Division | 0.58 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | SM/09677 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lejibheri, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000628/2021-2022 | 181/MD | 01/02/2022 | 01/01/2025 | MASUM ALI KHAN | 23.48 | 17.78 | 75.7 | 100
Total | [13 empty] | 39.13 | 27.82 | 71.09