## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Preparation of D.P.R. (Consultancy work) in connection with the Proposed Mini Pipe W/S Scheme for Uchitpur mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000418/2021-2022 | 1331/MD | 17/08/2021 | 27/08/2021 | GOBINDA MAITY | 1.94 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uchitpur water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001185/2021-2022 | 2532/W/MMD | 30/11/2021 | 04/12/2021 | MENAKA ENTERPRISE | 4.48 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uchitpur water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001141/2021-2022 | 2530/W/MMD | 30/11/2021 | 04/12/2021 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001827/2021-2022 | BP-2021-22-505 | 22/03/2022 | 22/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 8.13 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | For payment of liabilities. |  |  | VCH/001693/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.93 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas. Block - Sabang. District - Paschim Medinipur. |  |  | VCH/000454/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.93 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Uchitpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001198/2021-2022 | 157/W/MMD | 31/01/2022 | 31/05/2022 | P.K.ENGINEERING | 6.52 | 0 | 0 | 70
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Uchitpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001197/2021-2022 | 156/W/MMD | 31/01/2022 | 31/05/2022 | MENAKA ENTERPRISE | 6.52 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 2118/MD | 13/12/2021 | 13/12/2021 | Resource Division | 1.93 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uchitpur (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000858/2021-2022 | 422/MD | 04/03/2022 | 01/08/2022 | GOUTAM PARIA | 24.89 | 0 | 0 | 80
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09678 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uchitpur (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000630/2021-2022 | 183/MD | 01/02/2022 | 01/01/2025 | MASUM ALI KHAN | 37.49 | 0 | 0 | 100
Total | [13 empty] | 100.22 | 0 | 0