## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Mirjapur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001195/2021-2022 | 154/W/MMD | 31/01/2022 | 31/05/2022 | DIPALI CONSTRUCTION | 6.49 | 3.87 | 59.69 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Quotation for service connection charges of WBSEDCL at Lakshmichak,Andulia T/W-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001522/2021-2022 | 2003855188/Quot/03 | 10/03/2022 | 10/03/2023 | WBSEDCL | 0.13 | 0.13 | 100 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas. Block - Sabang. District - Paschim Medinipur. |  |  | VCH/000453/2022-2023 |  | 11/08/2022 | 11/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.31 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | For payment of liabilities. |  |  | VCH/001694/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.31 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Electric quotation Sabang CCC at Mirjapur Mini piped Water supply scheme under MMD PHE Dte |  |  | VCH/002771/2022-2023 | BP-2022-23-59 | 23/11/2022 | 23/11/2022 | WBSEDCL | 0.1 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Mirjapur water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001292/2021-2022 | 2518/W/MMD | 30/11/2021 | 04/12/2021 | OSMAN SEKH | 4.47 | 3.84 | 85.93 | 60
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 2119/MD | 13/12/2021 | 13/12/2021 | Resource Division | 0.31 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  |  | BILL/00245/2022-2023 |  | 01/02/2023 | 01/02/2023 | BADAL CHANDRA BERA | 0.07 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Mirjapur, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000857/2021-2022 | 421/MD | 04/03/2022 | 01/08/2022 | A R ENTERPRISE | 17.21 | 16.58 | 96.31 | 90
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09679 | New | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  |  | BILL/00239/2022-2023 |  | 31/01/2023 | 31/01/2023 | BADAL CHANDRA BERA | 0.63 | 0 | 0 | 0
Total | [13 empty] | 30.04 | 24.42 | 81.29