## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Preparation of D.P.R. (Consultancy work) in connection with the Proposed Mini Pipe W/S Scheme for Chaulkuri mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000420/2021-2022 | 1334/MD | 18/08/2021 | 28/08/2021 | GOBINDA MAITY | 3.06 | 3.06 | 99.91 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 3 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001129/2021-2022 | 2508/W/MMD | 30/11/2021 | 04/12/2021 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001134/2021-2022 | 2504/W/MMD | 30/11/2021 | 04/12/2021 | P.K.ENGINEERING | 4.47 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 4 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001128/2021-2022 | 2510/W/MMD | 30/11/2021 | 04/12/2021 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001131/2021-2022 | 2506/W/MMD | 30/11/2021 | 04/12/2021 | P.K.ENGINEERING | 4.47 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001819/2021-2022 | BP-2021-22-505 | 22/03/2022 | 22/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 15.57 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Quotation bill of WBSEDCL for application no 2003798482/2003798478/2003798131/2003798158/2003798182/2003798165 |  |  | VCH/005612/2021-2022 | BP-2021-22-72 | 07/03/2022 | 07/03/2022 | WBSEDCL | 0.76 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | For payment of liabilities. |  |  | VCH/001697/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.54 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -IV at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-152/W/MMD, DT.-31/01/2022) |  |  | VCH/005603/2021-2022 | BP-2021-22-119 | 17/03/2022 | 17/03/2022 | JAGANNATH ENTERPRISE | 3.87 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001190/2021-2022 | 149/W/MMD | 31/01/2022 | 31/05/2022 | BUSR ENGINEERING | 6.54 | 6.54 | 100 | 0
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -III at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001192/2021-2022 | 151/W/MMD | 31/01/2022 | 31/05/2022 | MANORANJAN DEY | 6.55 | 6.42 | 98.08 | 0
12 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001191/2021-2022 | 150/W/MMD | 31/01/2022 | 31/05/2022 | KAMAKSHYA ENTERPRISE | 6.59 | 6.48 | 98.29 | 0
13 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -IV at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001193/2021-2022 | 152/W/MMD | 31/01/2022 | 31/05/2022 | JAGANNATH ENTERPRISE | 6.51 | 2.63 | 40.35 | 0
14 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-IV), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000906/2021-2022 | 524/MD | 21/03/2022 | 18/08/2022 | BISWAJIT BAG | 38.24 | 35.36 | 92.46 | 0
15 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 2126/MD | 14/12/2021 | 14/12/2021 | Resource Division | 5.54 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000903/2021-2022 | 521/MD | 21/03/2022 | 18/08/2022 | USHA CONCERN | 44.75 | 41.63 | 93.02 | 92
17 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  |  | BILL/00239/2022-2023 |  | 31/01/2023 | 31/01/2023 | BADAL CHANDRA BERA | 0.63 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000904/2021-2022 | 522/MD | 21/03/2022 | 18/08/2022 | BISWAJIT BAG | 42.43 | 39.16 | 92.3 | 100
19 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chaulkuri & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09681 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-III), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000905/2021-2022 | 523/MD | 21/03/2022 | 18/08/2022 | BISWAJIT BAG | 49.24 | 47.33 | 96.12 | 100
Total | [13 empty] | 253.73 | 188.61 | 74.33