## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | Service connection charge of WBSEDCL at Fatechak, Sabang | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001033/2021-2022 | 2003774921/Quot/03 | 16/12/2021 | 16/12/2022 | WBSEDCL | 0.13 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Fate Chak water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001132/2021-2022 | 2520/W/MMD | 30/11/2021 | 04/12/2021 | P.K.ENGINEERING | 4.47 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | For purchasing of liabilities. |  |  | VCH/001699/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.67 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001820/2021-2022 | BP-2021-22-505 | 22/03/2022 | 22/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.87 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. |  |  | VCH/000450/2022-2023 |  | 10/08/2022 | 10/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.67 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Fate Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001177/2021-2022 | 123/W/MMD | 24/01/2022 | 24/05/2022 | SOUMEN ELECTRIC | 6.55 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 2117/MD | 13/12/2021 | 13/12/2021 | Resource Division | 0.67 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | SM/09682 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Fate Chak, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000629/2021-2022 | 182/MD | 01/02/2022 | 01/01/2025 | MASUM ALI KHAN | 21.15 | 0 | 0 | 100
Total | [13 empty] | 38.17 | 0 | 0