## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Naoyagan & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000449/2021-2022 | 1276/MD | 05/08/2021 | 15/08/2021 | GOBINDA MAITY | 2.11 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Naoyagan water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001138/2021-2022 | 2528/W/MMD | 30/11/2021 | 04/12/2021 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Naoyagan water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001140/2021-2022 | 2526/W/MMD | 30/11/2021 | 04/12/2021 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-145/W/MMD, DT.-31/01/2022) |  |  | VCH/005604/2021-2022 | BP-2021-22-118 | 17/03/2022 | 17/03/2022 | PRANAB KUMAR DAS | 4.13 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. |  |  | VCH/000449/2022-2023 |  | 10/08/2022 | 10/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.06 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Naoyagan & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. |  |  | VCH/001396/2021-2022 | BP-2021-22-388 | 18/02/2022 | 18/02/2022 | GOBINDA MAITY | 0.32 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001824/2021-2022 | BP-2021-22-505 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 8.11 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | For payment of liabilities. |  |  | VCH/001700/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.92 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001186/2021-2022 | 145/W/MMD | 31/01/2022 | 31/05/2022 | PRANAB KUMAR DAS | 6.51 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001187/2021-2022 | 146/W/MMD | 31/01/2022 | 31/05/2022 | BHABANI PRASAD MANNA | 6.56 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 2125/MD | 14/12/2021 | 14/12/2021 | Resource Division | 2.92 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Naoyagan (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000760/2021-2022 | 344/MD | 21/02/2022 | 21/07/2022 | SANKAR PRASAD MAITY | 41.8 | 0 | 0 | 70
13 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Naoyagan (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000759/2021-2022 | 343/MD | 21/02/2022 | 21/07/2022 | SANKAR PRASAD MAITY | 43.79 | 0 | 0 | 100
14 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09683 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk) | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 14/04/2025 | A-PLUS | 22 | 0 | 0 | 100
Total | [13 empty] | 150.16 | 0 | 0