## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | Service connection charge of WBSEDCL at Khunkhunia, Sabang | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001032/2021-2022 | 2003774931/Quot/03 | 16/12/2021 | 16/12/2022 | WBSEDCL | 0.13 | 0.13 | 100 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Khunkhunya & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000448/2021-2022 | 1275/MD | 05/08/2021 | 15/08/2021 | GOBINDA MAITY | 1.67 | 1.61 | 96.58 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Khunkhunya water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001139/2021-2022 | 2534/W/MMD | 30/11/2021 | 04/12/2021 | MENAKA ENTERPRISE | 4.47 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | For payment of liabilities. |  |  | VCH/001701/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.27 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001822/2021-2022 | BP-2021-22-505 | 25/03/2022 | 25/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.66 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Khunkhunya, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001179/2021-2022 | 125/W/MMD | 24/01/2022 | 24/05/2022 | M.S.ENTERPRISE | 6.52 | 6.42 | 98.38 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 2114/MD | 13/12/2021 | 13/12/2021 | Resource Division | 1.27 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | LOAD ENHANCEMENT OF KHUNKHUNYA MINI WATER SUPPLY SCHEME , SCHEME CODE SM/09684, COSUMER ID 20350372, CHANDKURI CCC [ ENTERED MB NO 3580, PAGE 13-14 ] |  |  | BILL/00857/2023-2024 | BP-2023-24-128 | 13/07/2023 | 13/07/2023 | WBSEDCL | 0.37 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Khunkhunya & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09684 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza ¿ Khunkhunya, Block ¿ Sabang, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000690/2021-2022 | 287/MD | 15/02/2022 | 15/07/2022 | SAI TUBE CO. | 42.01 | 39.04 | 92.94 | 100
Total | [13 empty] | 61.38 | 47.2 | 76.89