## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Bhabaninagar PWSS under Midnapore Sadar Block in Paschim Medinipur District | SM/09701 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Bhabaninagar PWSS Block-Midnapore Sadar in the District of Paschim Medinipur. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000412/2021-2022 | 2017/MD | 03/12/2021 | 01/02/2022 | MASUM ALI KHAN | 113.43 | 99.49 | 87.71 | 80
Total | [13 empty] | 113.43 | 99.49 | 87.71