## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 |  |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Manidaha PWSS under Midnapore Sadar Block in Paschim Medinipur District |  |  | Laying distribution pipe line, soil test and Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 350 CuM and staging height 20 mtr. as per approved drawing (No:- PC-I /OHR /12/2012 ) with allied works for Manidaha Water Supply Scheme within Medinipur Sadar Block including supply of all labour & materials under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000503/2021-2022 | 2245/MD | 28/12/2021 | 26/06/2022 | DIPAK KUMAR BAKLY | 230.53 | 5.54 | 2.4 | 70
2 |  |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Manidaha PWSS under Midnapore Sadar Block in Paschim Medinipur District |  |  | Retrofitting of Manidaha PWSS to accommodate FHTC in Midnapore Sadar block under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),JE1 Sadar Sub-division | ORD/000053/2022-2023 | 873/MD | 10/05/2022 | 29/06/2025 | DIPAK KUMAR BAKLY | 46.8 | 0 | 0 | 60
Total | [13 empty] | 277.33 | 5.54 | 2