## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District | SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza -Bara Bhursa in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-02) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000511/2021-2022 | 649/AE/MSSD | 14/12/2021 | 29/12/2021 | MAITY ENTERPRISE | 4.5 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District | SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza-Chhoto Bhursa in Kashijora PWSS in Salboni Block District Paschim Medinipore within Midnapore Division PHE Dte.(SL No-01) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000508/2021-2022 | 653/AE/MSSD | 14/12/2021 | 29/12/2021 | MAITY ENTERPRISE | 4.5 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District | SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza -Deulkunda in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-03) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000516/2021-2022 | 656/AE/MSSD | 17/12/2021 | 01/01/2022 | MAITY ENTERPRISE | 3.49 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District | SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza -Baradiha in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-04) |  |  | VCH/001649/2021-2022 | BP-2021-22-432 | 04/03/2022 | 04/03/2022 | MAITY ENTERPRISE | 4.44 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kashijora PWSS under Salbani Block in Paschim Medinipur District | SM/09705 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Mouza ¿Kashijora in Kashijora PWSS in Salboni Block District Paschim Medinipore within Midnapore Division PHE Dte.(SL No-01) | AE Kharagpur Sub-division,AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000343/2021-2022 | 532/AE/MSSD | 30/09/2021 | 15/10/2021 | MAITY ENTERPRISE | 4.85 | 0 | 0 | 0
Total | [13 empty] | 21.77 | 0 | 0